# Pennsylvania ARRA Weatherization State Plan

# Introduction

The American Recovery and Reinvestment Act (ARRA) provides $252.8 million for Pennsylvania’s Weatherization Assistance Program (WAP), which is designed to help low-income households decrease energy consumption and costs.  These resources will enable the Commonwealth to achieve greater energy independence, put more Pennsylvanians to work by increasing demand for skilled weatherization professionals and help vulnerable residents by reducing their energy bills.

As a result of these ARRA weatherization funds, Pennsylvania will:

- Reduce Pennsylvania energy usage by the equivalent of powering about 7,000 homes a year;

- Weatherize at least an additional 29,700 housing units over the next two to three years; and

- Put an estimated 940 Pennsylvanians to work.

The federal stimulus resources will make it possible for Pennsylvania to improve the return on public investment of the weatherization program by achieving greater energy savings with each unit serviced.  Greater savings will result from both a higher per-project expenditure cap and changes in how the program prioritizes the households selected and the weatherization work to be completed.

Pennsylvania will allocate its stimulus grant over three state fiscal years as allowed by the stimulus law: FY2009-10, FY2010-11 and FY2011-12.  The state intends to front-load expenditures to maximize the economic benefit to Pennsylvania workers and participating households, expending at least 50% of the ARRA allocation by September 30, 2010, and at least 80% by the end of the FY2010-11 fiscal year.  The contract period will be from the date that funds are first available to agencies through March 31, 2012.

Of the total $252.8 million ARRA grant, up to $8.3 million will be retained by the Department of Community and Economic Development (DCED) for the costs of program management, contract oversight, public reporting and other administrative activities and up to $20 million will be retained for training and technical assistance.  The balance of $224.5 million will be allocated to subgrantees.

Pennsylvania’s stimulus allocation is more than seven times larger than the Commonwealth’s FY2008-09 combined U.S. Department of Energy (DOE) and LIHEAP weatherization expenditures.  Even spread out over three years, the stimulus funds represent a massive investment in weatherization, which will require more capacity at all levels of the program’s operation.

As described in the pages that follow, Pennsylvania has a comprehensive plan for increasing weatherization activity while improving the program’s overall energy reduction performance on behalf of the low-income residents it is intended to serve.  Pennsylvania’s strategy includes:

- Distributing funding based on formula and establishing a process that enables agencies to demonstrate their production capacity and ability to meet energy savings targets for low-income populations;

- Expanding training opportunities and requirements;

- Prioritizing eligible households and work for the greatest return on investment;

- Ensuring program performance; and

- Strengthening oversight, monitoring and reporting.

These changes will be implemented as part of the state’s ARRA Weatherization Plan and many will also be carried over to the traditional weatherization program.  In addition, DCED will increase its own ability to provide technical assistance and oversight through the addition of staff, for the duration of the ARRA grant period, who have expertise in training coordination, financial management and program technical assistance.  DCED will also draw on consultants who can assist in evaluating agency capacity to increase production units and energy savings and potentially for monitoring and compliance, as described below.

# Expanding Statewide Capacity to Achieve Stimulus Goals

To ensure the success of Pennsylvania’s weatherization stimulus expansion, DCED will rely on the 42 traditional subgrantees and will add, pursuant to CFR 440.14 and 440.15 and DCED standard practice, the Pennsylvania Housing Finance Agency (PHFA) as an additional subgrantee upon submission and approval by DCED of PHFA’s qualifications to so serve for the purpose of serving multi-family units statewide.  If approved as a subgrantee, PHFA’s administrative costs will be paid from the state’s administrative fees under the program.  In addition, any subgrantee agency that opts to develop its own multi-family housing strategy involving publicly assisted (HUD or PHFA) housing will be required to set aside a portion of its grant to partner with PHFA.  Strategies involving non-public multi-family housing may necessitate other partnerships to implement.

Pennsylvania will allocate 10% of the funds to PHFA for this purpose with the balance of funding distributed among the other 42 subgrantee agencies using the standard distribution formula described below.  This is a distribution for the purpose of meeting the expectations of the DOE as well as the development of the agency management plans.  Funding will be awarded, adjusted or curtailed after the first quarter of production based upon specific performance standards.

The 42 subgrantee agencies will receive ARRA distribution of funds with an approximately three-year contract via the following standard formula:

- 50% of the funds based on each agency’s service area percentage of low-income population to the state total low-income population at 200% of the Federal Poverty Guidelines;

- 30% of the funds based on the each agency’s heating degree days to the state total; and

- 20% of the funds based on each agency’s 2008-09 funding level.

ARRA limits permit the average expenditure per household to be as high as $6,500.  Using that figure DCED has established a minimum production target for each agency resulting in total weatherization of approximately 30,000 units.  Agencies may use up to 5% of their funding distribution for necessary administrative costs and up to 1% for training and technical assistance costs.

DCED reserves the right to add additional subgrantees if needed to meet production goals and to adjust agency allocations and redistribute funds based on agency production and expenditures over the three-year contract period.  A special condition citing the right to reduce a grant amount if an agency cannot meet its production goals and energy savings performance targets will be added to all agency contracts.  If existing agencies cannot establish the additional capacity required to fully utilize ARRA funds, DCED will reach out to other vendors.

# Increasing Minority and Women Business Enterprise (MWBE) Participation

As agencies increase their production capacity, it is important to ensure participation of minority- and women-owned business enterprises (MWBEs).  Consistent with Executive Order 2004-6 issued by Governor Rendell on April 15, 2004, DCED will require agencies to establish MWBE programs and receive approval of their program plans.

# Prioritizing Households and Weatherization Work

As allowed under federal law, the Pennsylvania WAP will maintain eligibility up to 200% of the federal poverty level and the maximum allowable average weatherization cost per dwelling will be $6,500.  To ensure the greatest number of eligible high-end energy users are served, the program will permit units to be re-weatherized as long as the initial weatherization activity occurred before September 30, 1994 (as allowed under federal law).

To achieve the greatest possible impact on eligible households and in reducing aggregate energy use and cost, the state will implement several new measures to determine how eligible households and eligible work are prioritized.

# Prioritizing Households

Weatherization services have the greatest potential to save money and drive down energy use when they are first directed to the households that have the most extreme energy usage.

Since 2007-08, the WAP has incorporated procedures to identify high energy use households and included this factor in the weighting formula that determines overall priority.  Beginning in 2009-10, DCED will further refine its prioritization process to place greater emphasis on this category of need.

DCED will allow exceptions to the prioritization process for agencies that develop a plan to target concentrated pockets of eligible clients in a specific neighborhood or block and thereby use WAP resources to maximize impact on a clearly defined geographic unit for the benefit of eligible residents.  DCED encourages agencies to consider this approach.

DCED will also establish provisions to ensure that agencies can address emergency situations and health and safety needs of eligible clients.

The revised prioritization system follows:

# First Priority Households

All weatherization agencies will be required to give first priority to eligible households who are LIHEAP Cash and Crisis grantees and LIHEAP high energy users.  DCED will provide agencies with the list of targeted households within the agency’s service area.  Households on this list must be exhausted before an agency can serve other clients with ARRA funds, including households on the agency’s waiting list who do not meet this criterion.

In determining whether an agency has conducted sufficient outreach to an eligible LIHEAP household, DCED will require agencies to keep a log of LIHEAP household contacts and to make at least two efforts to contact the household at a time the client is most likely to be available.  The state will also send a mailing to all households that fall under this priority criterion advising them of the availability of weatherization services and who to contact in their region for additional information.

DCED will develop a coordinated outreach program with interested partners.  These partners will include media, DEP, PUC, utilities, colleges and universities.

Agencies will use the weighting scale described below to prioritize among the LIHEAP clients eligible for first-priority use of ARRA funds.

DCED will track each agency’s performance on the percentage of targeted clients whose units are successfully weatherized.

# Prioritization of Additional Households

In addition to establishing a set of first-priority clients as described above, DCED will also amend its weighting formula for use by agencies in prioritizing households.  The changes increase the emphasis on energy use, energy burden and low-income status:

| Category | 2008-09 Priority Points | 2009-10 / ARRA Priority Points |
| --- | --- | --- |
| Age | Up to 5 points for each member of the family based on the member’s age (highest point values for senior citizens and young children) | Total of 4 points if the household contains any members age 0 to 12 or age 60+ Total of 0 points if the household does not contain any members in those age groups |
| Disability | One point for family member with a disability | No change |
| Occupants | Up to 5 points based on the total number of occupants in the household | No change |
| Waiting time | Up to 5 points based on the total time that the client has been waiting for service | 0 points |
| High use | 2 points if the client’s fuel use exceeds: 20,997 Kwh for electricity 1,065 therms for natural gas 780 gallons for oil 5 cords for wood 1,093 gallons for propane 5 tons for coal | High use will result in a 15-point allocation |
| High burden | 1 point if the client’s annual energy costs are equal to or exceed 25% of the client’s annual income | High burden will result in a 10-point allocation |
| Poverty level | Up to 4 points based on the percent of the federal poverty level represented by the client’s income level | Up to 8 points based on the percent of the federal poverty level represented by the client’s income level: 8 points: Under 75% 6 points: 75%-100% 4 points: 101%-125% 2 points: 126%-150% 0 points: Above 150% |
| Other measures of high need | N/A | 3 points if the household is participating in a utility’s Customer Assistance Program (CAP) or receives a hardship fund grant Note that LIHEAP participants are automatically treated as a high-priority WAP applicant |

# Prioritizing Weatherization Work

The expansion of Pennsylvania’s weatherization program is occurring in a context of new high-performance energy technology and emerging best practices for residential energy efficiency and conservation.  To reflect the changing realities of the field, DCED will work to enhance many current WAP practices.

# Energy Audits & Work Prioritization

DCED in partnership with stakeholder representatives will evaluate the energy audit protocols currently approved for use in Pennsylvania to determine whether improvements or updates are warranted.  Specific attention will be given to energy audit protocols used to analyze building energy usage and set priorities for weatherization work for:

- One-to-four unit buildings

- Multi-family buildings

- Mobile homes

In addition to making certain that energy use analysis instruments are state-of-the-art, the revision will be specifically geared to ensuring the highest and best use of all weatherization resources in reducing energy use and costs.  Upon completion of its review, DCED will publish any draft revisions to its audit protocols and receive public comment before finalizing the new tools and priority standards.

Replacement of light bulbs and installation of a load controller receiver, which allows a resident to determine when individual appliances turn on and off in order to make efficient use of electricity and purchase power only when needed, will become standard protocol wherever possible.

To that end, the WAP will also implement strong coordination with programs established under Pennsylvania’s new energy efficiency and conservation law, known as Act 129.  One component of the law is the requirement that electric companies fund conservation services in households that may complement the weatherization program’s activities.  These services will be integrated into existing weatherization visits to the greatest extent possible in order to make the maximum energy conservation impact on eligible households; work will be completed by a single subgrantee, and billed back to the respective program (WAP or Act 129).  Work conducted under and billed to the WAP will not count towards the Act 129 requirements of the utilities.

Agencies will provide information in their management plans regarding how they will coordinate their weatherization programs with existing public utility universal service programs such as Customer Assistance Programs (CAPs), the Low Income Usage Reduction Program (LIURP), and utility initiated Hardship Funds.

# Standards for Weatherization Work

DCED will also amend its Pennsylvania Weatherization Standards field guide to establish a maximum cost for each element of approved work (recognizing that regional cost differences exist throughout the Commonwealth).  Draft maximum cost standards will be made available for public review and comment before being finalized.  The revised field guide will also set forth certain expenditures or weatherization work which will require DCED approval prior to execution.

# Work on Rental Units

Federal regulations specify that “no undue or excessive enhancement shall occur to the value of the dwelling units” in the case of rental housing.  To comply with that goal, Pennsylvania will require subgrantees to solicit an investment in the weatherization work from building owners when assisting rental units.  Owners who are not themselves eligible for WAP assistance are required to invest in the cost of the weatherization services provided to their buildings if:

- The total value of the work is greater than or equal to $4,000; or

- The work includes installation of a new furnace, water heater or refrigerator.

The minimum investment that owners must provide is 25% for buildings with fewer than 50 units and 35% for buildings with 50 units or more.  Revenue collected as a result of this change will provide additional weatherization services to Pennsylvania households.  DCED will establish policies for collecting owner contributions, and will establish a waiver process that subgrantees must follow for owners who cannot meet the required investment level.

# Training Auditors and Installers

The federal stimulus expansion of Pennsylvania’s weatherization program will require an estimated 940 additional trained workers from energy auditors to contractors to inspectors.  Although the use of stimulus funds is temporary in nature, the demand for a skilled weatherization workforce is expected to be long-lasting due to the growing green-collar economy.

# Expanding Training Capacity

Increasing the WAP workforce will require rapid expansion of training opportunities for weatherization workers.  The weatherization program is committed to providing training opportunities throughout the Commonwealth so that residents from all regions have access to jobs.  To the greatest extent possible, Pennsylvania and its training providers will take advantage of distance learning to maximize the number of locations where participants can receive training.  Field work, a required component of weatherization training, will be coordinated with agencies in each region, and both field work and on-site training will be emphasized.

The Pennsylvania ARRA WAP budget includes approximately $20 million to establish training that serves the WAP and creates an infrastructure for other public and private-sector weatherization training.  These resources will be used to pay for all training costs for the WAP.  The funding will be administered by the Pennsylvania Department of Labor & Industry (L&I), which is responsible for the Commonwealth’s workforce development system.

The WAP has traditionally relied on the training provided by the Weatherization Training Center (WTC) in Williamsport, North Central PA.  It is anticipated that the WTC, and potentially other qualified trainers, will increase their capacity to train workers as well as additional trainers.

In increasing the weatherization workforce, Pennsylvania encourages agencies to rely on the traditional workforce development pathways, including the CareerLink system and trade union apprenticeships as well as the welfare-to-work system in order to recruit workers.  To improve the ability of agencies to rely on these multiple pathways, L&I will provide pre-training assistance to weatherization training applicants as needed.

# Training Requirements

L&I will establish state training standards and certification standards for workers performing various weatherization functions.  The training standards will be adopted by any additional training providers that are selected to provide WAP training.  The certification will provide weatherization workers with an industry-recognized credential demonstrating their knowledge and skills.

Beginning in 2009-10, training is required for all auditors and installers, regardless of whether the individual is an employee of an agency or a contractor or subcontractor operating on behalf of an agency.  Agencies will have the option of including compensation for employee, contractor or subcontractor training time in their budgets.

Experienced weatherization workers will have the option to demonstrate their competency in mandatory skill areas without participating in the training courses.

Any changes to the list of required courses and timelines will be made available for public review before being finalized.

To the greatest extent possible, Building Performance Institute (BPI) training and certification will be provided to auditors, inspectors and monitors.

A detailed training plan can be found in the Training Plan attachment.

# Additional Workforce Considerations

As many agencies are preparing to significantly expand their staff and/or contractor pool, DCED advises that agencies conduct a background check on employees and contractors who will be used to deliver ARRA weatherization services.

# Ensuring High Performance Throughout the Weatherization System

DCED will establish new provisions to enhance program efficiency, effectiveness and accountability.

# Streamlining Purchasing and Contracting

All WAP subgrantees will participate in a statewide procurement process for materials and equipment.  This purchasing program is intended to reduce the costs borne by subgrantees in order to maximize the amount of weatherization work that can occur.  DCED will consider waivers to this requirement for exceptional circumstances. The statewide procurement process will apply to agencies and their subcontractors.  For materials and equipment that are not required to be purchased or are not available through the statewide procurement process, DCED will require the agency and their subcontractors to obtain at least three arm’s-length bids.  This bidding requirement will be included in all contracts used by subgrantees.

# Timeline Requirements and Production Goals

All agency production plans will include monthly production goals subject to approval by DCED.  Agencies that do not meet their quarterly production targets beginning with the first quarter of production and every quarter thereafter, or that do not expend at least 50% of their total ARRA allocation by September 30, 2010, may be replaced or have their funding adjusted by DCED, in a manner consistent with applicable DOE regulations.

# Production Timeline

Agencies will substantially increase their operational capacity in order to meet their stimulus production goals.  This will require immediate purchase of equipment and materials.

Agencies will submit a three-year budget based on the distribution formula.  The agency’s production timeline must demonstrate capacity to expend at least 50% of the agency’s total ARRA funds by September 30, 2010.  Spending authority will be constrained to a maximum only to that level of funding.  Agencies can request between 25% to 50% of the first-year budget as an up-front or advance payment by providing a budget for the use of the advance payment and a budget narrative describing the need for the advance.  Agencies will propose plans of expending at least 80% of the funds by June 30, 2011; and 100% by March 31, 2012, if awarded.  Funds that have not been allocated to any subgrantee not meeting performance requirements will be reallocated by DCED to other subgrantees in accordance with DOE regulations.

Ability to Implement Performance-Based System

Agencies and their participating contractors will be evaluated on whether their initial performance meets capacity and production targets (i.e., number of staff hired and trained and the number of houses completed).  Energy reduction targets will be established when data are available after the first year, and performance relative to these targets will be the primary consideration for continued funding.  Continued program funding levels will be based on whether agencies have met their energy targets over a set period of time.  Energy targets will be weather-normalized and will take into account sale or turnover of weatherized units that occur during the monitoring period.  DCED will publish a draft performance contracting plan during FY 2009-10 and receive public input before making any revisions and publishing final provisions.  Agency proposals should demonstrate the capacity to establish internal procedures to ensure the validity of information collected.

Beginning immediately, all clients will be required to provide approval for DCED to receive their monthly energy usage data directly from the utility for at least one year after weatherization occurs.

# Ensuring Client Commitment to Energy Conservation

Agencies will continue to provide clients with education on ways to reduce their energy use and costs.  In addition, clients must sign a compact setting out their commitment to conservation.  DCED will develop a compact for use by agencies, which will include commitments such as:

- Setting thermostat back 5 to 10 degrees at night or when no one is home during the heating season;

- Using shades or curtains to reflect out the summer sun during the heat of the day;

- Checking furnace filters monthly during the heating or cooling season, and changing or cleaning them as necessary;

- Opening all registers, and not obstructing them with furniture or rugs;

- Checking prime and storm windows regularly during cold weather to make sure they are closed; and

- Servicing oil-fired heating systems annually.

Agencies will provide a plan documenting how they will work with other appropriate entities to facilitate client follow-up when energy usage increases.  Although weatherization funds cannot be used for agency follow-up, it is highly recommended that agencies re-evaluate their existing client education component and determine how to partner within the community to advance the client education process.  DCED and other partners will provide support on a statewide level to develop an effective strategy to support and coordinate efforts.

# Enhancing Oversight of the Weatherization Assistance Program

An updated “Monitoring Guidelines and Procedures” document was distributed before the beginning of the 2008-09 program year in order to standardize monitoring procedures and instruments and provide agencies with a clearer understanding of the process and content of on-site monitoring.

DCED will enhance its monitoring by establishing a monitoring, compliance and reporting system that includes:

- Inspection of 10% of all units (in progress) focusing on the energy audit and work prioritization; and

- Inspection of 10% of all units (completed) focusing on the installation work and its consistency with the energy audit.

Monitoring by DCED will include all of the following:

- Current Quality Assurance: Field inspections of current year jobs, including jobs in progress rather than just completed jobs.

- Current Year Documentation: In the files for completed jobs.

- Current Year Blower Door Readings: pre, post and the percent reduction averaged per house.  This information will be compared to that of other agencies working in comparable housing stock in order to monitor quality of the work, as infiltration reduction correlates to energy savings in space heating.

- Current Year Cost Per House: To ensure reasonableness.

- Financial Monitoring: A financial monitoring team will spot-check agencies and provide technical assistance to strengthen internal controls.

There are currently three full-time staff assigned to conduct on-site monitoring on behalf of DCED.  To meet the needs of the stimulus expansion, DCED will hire eight additional monitors possessing the appropriate qualifications.

Local agencies are required to inspect 100% of all completed units.

No dwelling unit may be reported to DCED as completed until a final inspection is performed and signed by a designated Quality Control person.  The results of the inspection must be provided to the client for their review and sign-off.  Any need for corrective work should be noted with the client at this time. If no additional work is necessary, a signed and dated Client Completion form is required.  Current forms may be adapted to meet both of these requirements (i.e., quality control inspection and client completion).  Quality control inspections must be performed by a qualified person not involved in the actual installation.

If a quality inspection and/or client sign-off cannot be performed due to an uncooperative client once the work is completed, two phone attempts on different days at different times of the day to secure these sign-offs must be documented. Final written notification is to be sent to the client indicating that, if no response is received within a specified period of time, the job will be closed and no further action will be taken on behalf of the client.

# Contract Compliance Requirements

All agencies will be required to maintain internal controls that include a contract compliance function that does not report to the agency’s Weatherization Director.  Agencies will be required to separate purchasing from the rest of weatherization functions.

# Purchasing Systems

Purchasing systems should be designed to track inventory usage and expense.  Once the inventory function of the Hancock Energy System (HES) software is enabled, agencies will be able to use it to monitor inventory down to the individual house level, and DCED will monitor purchasing within each agency and across agencies.

# Financial Disclosure

All subgrantees will be required to file financial disclosure statements for officers and directors.

# Conflicts of Interest

All subgrantee management staff and purchasing personnel will be required to file conflict of interest statements.

# Annual Energy Savings Impact Evaluation

The best way to ensure that the weatherization program is achieving its goals and that there is no waste or other problems occurring is to have the program independently evaluated every year.  DCED will issue an Request for Proposal seeking an external evaluation from a leading national evaluator.  The evaluation will measure energy savings down to the subcontractor level and report on energy saved in relation to the cost per house.  The evaluation results will inform DCED’s monitoring and technical assistance.

# Oversight and Reporting

Pennsylvania is committed to accountability and transparency in the use of all ARRA funds.  The Commonwealth has:

- Established a Recovery website at www.Recovery.PA.gov to make information on the allocation and impact of stimulus funding available to the public;

- Appointed a federal stimulus Chief Accountability Officer;

- Appointed a federal stimulus Chief Implementation Officer; and

- Convened by Executive Order a Pennsylvania Stimulus Oversight Commission

Pennsylvania and the federal government will institute enhanced reporting by subgrantees to track program effectiveness in terms of meeting major stimulus goals: energy conservation, job creation and provision of services to help vulnerable residents.

The United States Department of Energy has also indicated that it will require financial and progress reports from the state, which will, at minimum, include reporting on the following measures:

- Jobs created at the state agency level

- Jobs created using state contractors

- Jobs retained at the state agency level

- Jobs retained with state contractors

- Jobs created at the local agency level

- Jobs created using local agency contractors

- Jobs retained at the local agency level

- Jobs retained with local agency contractors

- Number of weatherized units in progress

- Number of completed units in progress

- Number of client outreach contacts

- Number of energy conservation education contacts

- State desk monitoring/oversight visits

- State on-site monitoring/oversight visits

- Hours trained at the state agency

- Hours trained at the local agency

- Year-to-date expenditures

- Equipment units purchased that are more than $5,000

Subgrantees also will be required to submit to DCED, in a timely and complete manner, any other data, information or documents necessary for the state to comply with any other reporting requirements imposed on it by the federal government (such as OMB).

# Additional Components of the State Plan

# Authorization

The Energy Conservation in Existing Buildings Act of 1976, Title IV of the Energy Conservation and Production Act (referred to as “the Act”), authorized the Federal Energy Administration, which is now part of DOE, to establish a Weatherization Assistance Program to aid low-income households, with emphasis on those who are elderly and handicapped, to decrease fuel consumption and related energy costs.

ARRA of 2009, Public Law 111-5, appropriates funding for DOE to issue/award formula-based grants under the Weatherization Assistance Program.

In the Commonwealth of Pennsylvania, the Secretary of DCED, as the designee of the governor, applies for, receives and administers these funds.  The funds are distributed by DCED to local governments and non-profit organizations such as Community Action Agencies.

Each federal fiscal year a State Plan is required for continued participation in the program.  This document constitutes the proposed Pennsylvania State Plan for ARRA funds for the Weatherization Assistance Program for federal program period 2009-2012.  As such, it establishes the number of homes to be weatherized within the limits of available resources, the specific energy conservation measures to be undertaken, eligibility requirements, projected energy savings, program implementation strategies, specific training initiatives, reporting requirements, monitoring mandates, and specific contractual language addressing compliance issues with production schedules and other DOE program requirements.  The content of the proposed plan are derived where applicable from DOE regulations as contained in the Federal Register, 10 CFR Part 440 Final Rule, published February 1, 2002, and specific DOE instructions from Funding Opportunity Number: DE-FOA-000051.

In accordance with DE-FOA-0000051, DCED submitted its initial application for weatherization assistance funds under the ARRA on March 23, 2009.  On March 27, 2009, DCED was notified of receipt of 10% of its grant award, or $25,279,306.

# Davis-Bacon Act

DCED will provide contractual language that all laborers and mechanics employed by contractors and subcontractors on projects funded directly by or assisted in whole or in part by and through funding appropriated by ARRA are paid wages at rates not less than those prevailing on projects of a character similar in the locality (Davis-Bacon Act).  The U.S. Department of Labor or its designee will make the prevailing wage determinations, and the WAP will provide training in Davis-Bacon requirements.

# Compliance with the Davis-Bacon Act is required. 	Agencies will describe their processes to comply based on the instructions found on the DOE website at http://apps1.eere.energy.gov/weatherization/pdfs/energyweb_bullets.pdf.

# Lead Safe Weatherization

The PA Weatherization Assistance Program will implement revised rules for Lead Safe Weatherization (LSW) as per guidance provided in DOE Weatherization Program Notices 08-6 and 09-6.  Lead safe weatherization methods will be updated in the “PA Weatherization Standards and Field Guide” as identified in the On-File Information of this plan.

# Policy Advisory Council

# In accordance with 10 CFR, Section 440.17, DCED established a Weatherization and Energy Conservation Policy Council.  The Weatherization and Energy Conservation Policy Council advises DCED on issues related to the conduct and administration of the WAP.  The proposed plan is reviewed by the Policy Council and, where feasible, their comments and recommendations are included prior to submission of the plan to the DOE.  The Council includes representatives of energy advocacy groups, social service agencies, electric utilities, utility associations, subgrantees and other governmental agencies.  The Policy Council plans to meet two to three times per year.  A copy of the current membership is provided in the attachment section of this plan.

7 August 2009